## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2023
PROVINCE: PANGASINAN |  |  | QUARTER: | 2
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Emerging and Re-emerging Dseases | Entire Mapandan, Pang. | 500000 |  | 2023-12-31
Econimic Development
Improvement of Multi-Purpose covered court (Baloling) | Brgy. Baloling, Mapandan | 500000 |  | 2023-12-31
Improvement of Multi-Purpose covered court (Sta. Maria) | Brgy. Sta. Maria, Mapandan | 500000 |  | 2023-12-31
Construction of One Stop Shop Building Phase 3 | Poblacion, Mapandan | 4000000 |  | 2023-12-31
Renovation of Mapandan Tennis Club Court | Poblacion, Mapandan | 500000 |  | 2023-12-31
Renovation of Plaza Café | Poblacion, Mapandan | 1000000 |  | 2023-12-31
Improvement Brgy. Road/Drianage-Maya St. Amanoaoac | Amanoaoac, Mapandan | 407091.65 |  | 2023-12-31
Improvement Brgy. Road/Drianage-Papata Ave. Apaya | Apaya, Mapandan | 407091.65 |  | 2023-12-31
Improvement Brgy. Road/Drianage-Caimito Ext. Aserda | Aserda, Mapandan | 500000 |  | 2023-12-31
Improvement Brgy. Road/Drianage-Orchid St. Nilombot | Nilombot, Mapandan | 700000 |  | 2023-12-31
Improvement Brgy. Road/Drianage-Bougainvellia St. Poblacion | Poblacion, Mapandan | 500000 |  | 2023-12-31
LGU payment of Loan | Mapandan, Pangasinan | 15730362.29 |  | 2023-12-31 | 47.12% | 7412929.93 |  | on going
Replacement of Blvd. Lights at Pandan Avenue | Mapandan, Pangasinan | 1000000 |  | 2023-12-31
Improvement of Mapandan Public Market | Poblacion, Mapandan | 1000000 |  | 2023-12-31
Environmental Management
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Local Budget Officer |  |  |  |  | Local Chief Executive
ANA MARICRIS B. NATAVIO
HON. KARL CHRISTIAN F. VEGA

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1