## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2023
PROVINCE: PANGASINAN |  |  | QUARTER: | 3
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Econimic Development
Improvement of Multi-Purpose covered court (Baloling) | Brgy. Baloling, Mapandan | 500000 | 2023-08-01 | 2023-12-31 | 0% |  |  | on going
Improvement of Multi-Purpose covered court (Sta. Maria) | Brgy. Sta. Maria, Mapandan | 500000 | 2023-08-01 | 2023-12-31 | 0% |  |  | on going
Construction of One Stop Shop Building Phase 3 | Poblacion, Mapandan | 3000000 |  | 2023-12-31 | 0%
Renovation of Mapandan Tennis Club Court | Poblacion, Mapandan | 500000 |  | 2023-12-31 | 0%
LDF-construction of Landbank ATM Hub | Poblacion, Mapandan | 400000 |  | 2023-12-31 | 0%
Improvement Brgy. Road/Drianage-Maya St. Amanoaoac | Amanoaoac, Mapandan | 407091.65 | 2023-08-01 | 2023-12-31 | 0% |  |  | on going
Improvement Brgy. Road/Drianage-Papaya Ave. Apaya | Apaya, Mapandan | 407091.65 | 2023-08-01 | 2023-12-31 | 0% |  |  | on going
Improvement Brgy. Road/Drianage-Caimito Ext. Aserda | Aserda, Mapandan | 500000 | 2023-08-01 | 2023-12-31 | 0% |  |  | on going
Improvement Brgy. Road/Drianage-Orchid St. Nilombot | Nilombot, Mapandan | 700000 | 2023-08-01 | 2023-12-31 | 0% |  |  | on going
Improvement Brgy. Road/Drianage-Bougainvellia St. Poblacion | Poblacion, Mapandan | 500000 | 2023-08-01 | 2023-12-31 | 0% |  |  | on going
Impro. Brgy Road/Drianage-Orchid St. Nilombot Phase 2 | Poblacion, Mapandan | 576000 |  | 2023-12-31 | 0%
LGU payment of Loan | Mapandan, Pangasinan | 17754362.29 | 2023-01-01 | 2023-12-31 | 70.52% | 12520444.18 |  | on going
Improvement of Mapandan Public Market | Poblacion, Mapandan | 1000000 |  | 2023-12-31 | 0%
Additional Illumination of Mapandan Town Plaza | Poblacion, Mapandan | 500000 |  | 2023-12-31 | 0%
Environmental Management
Total |  | 27244545.59 |  |  | 45.96% | 12520444.18
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Local Budget Officer | Municipal Accountant |  |  |  | Local Chief Executive
ANA MARICRIS B. NATAVIO
HON. KARL CHRISTIAN F. VEGA
RUTH B. SOTTO

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1