## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2024
PROVINCE: PANGASINAN |  |  | QUARTER: | 1
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Econimic Development
Construction of Perimeter Fence, Backfilling and Concreting of Super Rural Health Unit's Ground | Brgy. Torres, Mapandan | 1500000 |  |  |  | 0 |  | Not yet Implemented
Construction of Cross/Drainage Canal along Gondol Street , Primicias | Brgy. Primicias, Mapandan | 500000 |  |  |  | 0 |  | Not yet Implemented
Improvement/Extension of Office for MDRRM Command Center at Brgy. Poblacion | Brgy. Poblacion, Mapandan | 700000 |  |  |  | 0 |  | Not yet Implemented
Improvement/Re-painting of Roof of the Mapandan Municipal Hall | Brgy. Poblacion, Mapandan | 1700000 |  |  |  | 0 |  | Not yet Implemented
Re-conctruction of Drainage Canal along Pico Avenue at Brgy. Coral | Brgy. Coral, Mapandan | 500000 |  |  |  | 0 |  | Not yet Implemented
Construction of Covered Drainage Canal along Lawin Avenue at Brgy. Poblacion | Brgy. Poblacion, Mapandan | 500000 |  |  |  | 0 |  | Not yet Implemented
Procurement and Installation of Industrial Fan at Tulagan Multi-Purpose Gym | Brgy. Poblacion, Mapandan | 300000 |  |  |  | 0 |  | Not yet Implemented
Construction of Drainage Canal along Papaya Avenue, Apaya Phase 2 | Brgy. Apaya, Mapandan | 500000 |  |  |  | 0 |  | Not yet Implemented
Impro. Brgy Road/Drianage-Orchid St. Nilombot Phase 3 | Brgy.Nilombot, Mapandan | 1000000 |  |  |  | 0 |  | Not yet Implemented
LGU payment of Loan | Mapandan, Pangasinan | 21176026.09 | 2024-01-01 | 2024-12-31 | 18.48% | 3913591.41 |  | On going
Additional Illumination of Mapandan Town Plaza Phase 2 | Brgy. Poblacion, Mapandan | 571506.51 |  |  |  | 0 |  | Not yet Implemented
Environmental Management
TOTAL |  | 28947532.6 |  |  | 13.52% | 3913591.41
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Local Budget Officer | Municipal Accountant |  |  |  | Local Chief Executive
ANA MARICRIS B. NATAVIO
HON. KARL CHRISTIAN F. VEGA
RUTH B. SOTTO

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1