## Sheet1
ANNUAL GENDER AND DEVELOPMENT (GAD) ACCOMPLISHMENT REPORT
FY 2023
Region: 1
Province: PANGASINAN | [6 empty] | Total LGU Budget: P136,222,728
Municipality: Mapandan | [6 empty] | Total GAD Budget: P6,811,136.40
Gender Issue or GAD Mandate | GAD Objective (2) | Relevant LGU Program or Project (3) | GAD Activity (4) | Performance Indicator and Target (5) | Actual Result | Total Approved GAD Budget | Actual Cost or Expenditures | Variance Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
CLIENT-FOCUSED
1. Inadequate knowledge on Sexual education among high school students | To educate the students on sexual education in their well- living and sexuality | Information, Education and Communication Campaign on Health Program | Conduct IEC campaign through coordination with concerned School Heads | One (1) IEC campaigns conducted with 250 Grades 9 & 10 attendees/participants |  | 10000 | - | The fund was not utilized as the Municipality has maximized its resources. The LGU has continuous coordination with schools regarding Health Campaign Program of the Municipality.
July - December 2023
2. Inadequate blood supplies for emergency assistance for men and women (especially pregnant women) | To have sufficient blood supplies to be used for in need clients of Mapandan | Blood Letting IEC Program | Conducts blood letting activity quarterly | One (1) Blood letting activity conducted | 2 Blood letting Activity Conducted | 150000 | 150000
|  |  | Identify blood donors | 400 blood donors identified | 400 Blood Donors identified
January - December 203
3. Increase number of early marriages/teenage pregnancies by 10 percent and 5 percent live-in partners | To develop and integrate to the "would be couples" during PMOC lecture session the Parenting Capability and Responsible Parenthood Program; To improve moral values | Family Planning Program; Marriage Orientation and Counseling Service | Conduct PMC & orientation seminar to "would be couples" and promote the sacredness of marriage | 190 "would be couples attending PMOC Seminar" # of live-in couples informed/educated and married solemnize | 138 would be couples attended PMOC Seminar | 15000 | 15000
| To increase awareness on Sexual & Reproductive health among teenagers | Information Education & Communication campaign on health program | Conducts symposium on sexual & reproductive health through coordination with concerned school heads | 400 high school students attended symposium
|  |  |  | 190 would be couples served | 138 would be couples served
| To provide effective learning thru additional video materials for presentation | Understanding/lecture discussions on pre-marriage orientations & counseling of would be couples | Procurement of projector | January - December 2023
4. Lack of knowledge on motherhood & proper nutrition among pregnant women | To provide learning information on RPs, Health & Nutrition Program | Health and Nutrition Program & Responsible Parenthood | Lecture/IEC on responsible parenthood | No. of pregnant/s and lactating mothers attended/participated | 25 pregnants and lactating mothers attended/participated | 180000 | 180000
|  | Dietary supplementation programs for the target groups | Advocacy on the importance of the first 1000 days of child's life | January - December 2023
5. Limited access to poverty alleviation program | To cater the request if indigent families for financial assistance | Implementation of the devolved programs & services of MSWDO | Provision of financial assistance under AICS | 334 Individuals provided with Financial Assistance under AICS (Medical, Burial, Emergency Shelter Assistance) | 318 Individuals provided with Financial Assistance under AICS (Medical, Burial, Emergency Shelter Assistance) | 1000000 | 952000 | The remaining funds were saving expenditure.
|  |  |  | 100 Students provided with Educational Assistance | 100 Students provided with Educational Assistance | 300000 | 300000
January - December 2023
6. Increase number of dental problems among days care children | To address & reduce dental problem in children cause by improper information on oral & dental hygiene matters | Dental and Health program | Information dissimination & conducts of dialogue with parents in oral & dental hygiene matters | No. of Day Care Children served & parents Informed | 500 Day Care Children Served and parents informed | 71545 | 80376.63 | Additional Fund as the fund allocated is not sufficient to implement the program.
|  |  | Procurement & provision of dental kit | January - December 2023
7. Insufficient funds for Child Development Operation | To provide sufficient funds for Child Development Center Operations | Early Childhood Care & Development Program | Lobby to the LCE for the increase of child development workers honorarium | 14 of child development workers | 14 Child Development Workers | 887040 | 887040
January - December 2023
8. Insufficient benefits of Indigent Male by 1,740 and Female by 2,424 Senior Citizens | To implement programs and services of Senior Citizens mandated by law | Senior Citizens' Welfare Assistance | Grant the assistance and services intended for Senior Citizens | 15 barangays Senior Citizens served | Senior Citizens Served from 15 barangays | 1200000 | 1128493 | The remaining funds were saving expenditure.
January - December 2023
9. Prevalence of indigent out of school children grades 4-6 | To provide educational assistance among identified out of school children (grade 4-6) | Adopt "Batang Mahirap, Edukasyon Mo Sagot Ko" Program of PNP | Identify the beneficiaries of the program | One (1) indigent out of school/child | Not implemented | 10000 |  | No OSY identified for the program.
June - December 2023
10. Lack of awerness on the negative effects of illegal drug usage. | To maximize the knowledge & awareness of the students as well as the faculties | Symposium/lecture on said subject | Conducts of symposium/lecture (MADAC) | No. of symposium/lecture conducted | symposium/lecture was conducted | 250000 | 217206 | The remaining funds were saving expenditure.
January - December 2023
11. Inadequate of knowledge on environmental issues among children/household mothers. | To educate the children in the proper way/practice of solid waste management | Reactivation of Clean and Green program | Dialogue among Punong Barangays to educate the children for the program implementation of Clean and Green |  | 15 Barangays participated in the Clean and Green Program of the Municipality | 380000 | 380000
15 barangays participated in Clean & Green program
January - December 2023
12. Lack of knowledge on sports & teenage development for children & teenagers | To promote the value of sportmanship and to encourgae outdoor activities beneficial to the well-bing of the children & youth | Sports Development Program | Conducts of Early Childhood Care Development & Youth Development sessions and sport activities | 15 barangays participated | 15 Barangays Participated. | 568455 | 568455
No. of Youth Development Session & Sports Activities conducted
January - December 2023
13. Lack of awareness among PWDs on the Magna Carta for Person with Disabilities | To conduct orientation among potential PWD Members on R.A. 9442 "An Act Amending R.A. 7277, otherwise known as Magna Carta for Disabled Persons and for other purposes" | Capability Building for PWD | Information/Education Campaign/Dialogue | 45 of PWD participants attended January - December 2023 | 45 of PWD participants attended | 100000 | 100000
14. Insufficient budget to Phil. Health Program | To provide sufficient budget for Phil. Health program | Phil.Health program for indigent families | Increase of budget for Phil. Health Insurance Program and additional member or beneficiaries | No. of barangays availed of Phil. Health Insurance program | 15 Barangays availed of PhilHealth Insurance program | 566400 | 528000 | The remaining funds were saving expenditure.
|  |  |  | No. of Phil. Health beneficiaries | 98 PhilHealth Beneficiaries
January - December 2023
15. Lack of training/seminars of PNP Personnel of (FJGADPNCO) and partner agencies on GAD. | To improved and enchanced the Capability of PNP Personnel in handling/addressing Gender Based Violence | Seminar/trainings for PNP Personnel and parter agencies | Re-echo Gender Based Violence Trainings to women & men Pantawid Pamilyang Pilipino Program Beneficiaries; First aid basic life support | No. of seminars/trainings attended participated by PNP personnel & partner agencies | 24 Seminars/trainings re: Gender Based Violence attended by PNP Personnel | 50000 | 30000 | The remaining funds were saving expenditure.
January - December 2023
16. Institutionalization of women's welfare PAPS towards gender equality | to enhance capacities of women constituents, female headed families | Women's Month Celebration Livelihood/Programs/Project | women's forum on Gender-Based Violence (GBV) activities. Procurement of Advocacy Materials Provision of Economic Productivity | 100 Women Participated and benefited | 105 Individuals participated in the LGU-led activity for Women | 130000 | 199399 | Additional Fund as the fund allocated is not sufficient to implement the program.
|  | 18-day campaign to End Violence Against Women | Procurement of Advocacy T-Shirt and Materials women's forum on Gender-Based Violence (GBV) activities.
17. Finamcial Difficulties of parents in support to Children's Education | To Provide Support services to children's education | Educational Assistance | Provision of Educational Assistance | College Students has provided with educational assistance |  | 500000 |  | The fund was realigned to other program as the MSWD Office has already allocated fund for educational assistance.
18. Poor Capacities of Parents in providing early eduation due to domestic chores | To strengthen child development service in support to parents | Maintenance and Operation of Child Development Services | 14 CDC/CDW programs maintained | 14 CDC/CDW programs maintained | 14 CDC/CDW programs maintained | 30000 | 30000
19. Lack of fund for the repair and maintence of Child Development Centers | To strengthen child development service in Mapandan | Maintenance and Operation of Child Development Services | 14 Child Development Centers |  |  | 202696.4 |  | Minor repairs of CDCs were funded by the Barangay LGU and the fund was reverted to Construction of Child Develpoment Center in Barangay Golden.
Sub-total A | [5 empty] | 6601136.4 | 5745969.63
ORGANIZATION-FOCUSED
1. Lack of training of newly hired BSPO, BHW, BNS, MNAO & POPCOM Officer | To cater and accommodate the trainings of newly BSPOs/BHWs to enhance their awareness and understanding towards Responsible Parenthood & Family Planning matters and orientation and different programs of DOH and their roles and functions | Capacity Development Program for newly hired BSPO, BHW, BNS, MNAO & POPCOM Officer | Conduct trainings on RPS & Family Planning and orientation and different programs of DOH and their roles and functions | 30 Volunteers trained | 30 Volunteers trained | 80000 | 72641.75 | The remaining funds were saving expenditure.
January - December 2023
2. Lack of training regarding GAD Data Based Creation & Special protection of childrens against child abuse, exploitation & discremination act to partner agencies | To provide traning/convention for Juvenile Gender and Development Summit and other activities relative hereof. | Capacity Development Program/GAD Program | Attendance to training & development and others activities realtive hereof | No. of participants attended training | 10 Participants attended training | 50000 |  | No Training invitation was received by the LGU.
January - December 2023
3. Inadequate training & seminars of ECCD providers | To conduct training/seminars on EO 15 and ECCD new tool | Capability Development Program | Provide training/seminars on EO15 to ECCD providers in the delivery of services during the pandemic | No. of ECCD providers participated & trained | 15 ECCD providers/CDWs attended training | 50000 | 50000
January - December 2023
4. Expired license & Certificate of BLS of RHU personnels | To have additional skills & knowledge regarding BLS and with renewal license | Updating & Awarding of Certification of Basic Life Support (BLS) training of RHU personnel | Training of RHU personnels & others concerned agencies on BLS | No. of RHU personnel & other concerned agencies trained | 85 RHU personnel attended training on BLS | 30000 | 201404 | Additional Fund as the fund allocated is not sufficient to implement the program.
January - December 2023
Sub-total B | [5 empty] | 210000 | 324045.75
GRAND TOTAL | [5 empty] | 6811136.4 | 6070015.38
Prepared by: LEONORA D. DOMINGUEZ, RSW, MSWDO Chairperson, GFPS-TWG |  | Approved by:
RAMIL S. DE VERA, RSW |  | HON. KARL CHRISTIAN F. VEGA
MSWD Officer |  | Municipal Mayor