## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2023
PROVINCE: PANGASINAN |  |  | QUARTER: | 4
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Econimic Development
Improvement of Multi-Purpose covered court (Baloling) | Brgy. Baloling, Mapandan | 500000 | 2023-08-01 | 2023-12-31 | 100% | 496256.93 |  | COMPLETE
Improvement of Multi-Purpose covered court (Sta. Maria) | Brgy. Sta. Maria, Mapandan | 500000 | 2023-08-01 | 2023-12-31 | 100% | 475403.1 |  | COMPLETE
Construction of One Stop Shop Building Phase 3 | Poblacion, Mapandan | 3000000 | 2023-10-01 | 2023-12-31 | 100% | 2997955.38 |  | COMPLETE
Renovation of Mapandan Tennis Clubhouse | Poblacion, Mapandan | 500000 | 2023-12-01 | 2024-01-15 | 0% | 0 |  | ON GOING
LDF-construction of Landbank ATM Hub | Poblacion, Mapandan | 400000 | 2023-10-01 | 2023-12-31 | 100% | 398401.57 |  | COMPLETE
Improvement Brgy. Road/Drianage-Maya St. Amanoaoac | Amanoaoac, Mapandan | 407091.65 | 2023-08-01 | 2023-12-31 | 100% | 406245.52 |  | COMPLETE
Improvement Brgy. Road/Drianage-Papaya Ave. Apaya | Apaya, Mapandan | 407091.65 | 2023-08-01 | 2023-12-31 | 100% | 396277 |  | COMPLETE
Improvement Brgy. Road/Drianage-Caimito Ext. Aserda | Aserda, Mapandan | 500000 | 2023-08-01 | 2023-12-31 | 100% | 499446.94 |  | COMPLETE
Improvement Brgy. Road/Drianage-Orchid St. Nilombot | Nilombot, Mapandan | 700000 | 2023-08-01 | 2023-12-31 | 100% | 699280.27 |  | COMPLETE
Improvement Brgy. Road/Drianage-Bougainvellia St. Poblacion | Poblacion, Mapandan | 500000 | 2023-08-01 | 2023-12-31 | 100% | 496710.97 |  | COMPLETE
Impro. Brgy Road/Drianage-Orchid St. Nilombot Phase 2 | Poblacion, Mapandan | 576000 | 2023-08-01 | 2023-12-31 | 100% | 575406.62 |  | COMPLETE
LGU payment of Loan | Mapandan, Pangasinan | 17754362.29 | 2023-01-01 | 2023-12-31 | 100% | 17595218.4 |  | COMPLETE
Improvement of Mapandan Public Market Phase III | Poblacion, Mapandan | 1000000 | 2023-12-01 | 2023-12-31 | 100% | 999355.01 |  | COMPLETE
Additional Illumination of Mapandan Town Plaza | Poblacion, Mapandan | 500000 | 2023-12-01 | 2023-12-31 | 100% | 497686.45 |  | COMPLETE
Environmental Management
Total |  | 27244545.59 |  |  | 97.39% | 26533644.16
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Local Budget Officer | Municipal Accountant |  |  |  | Local Chief Executive
ANA MARICRIS B. NATAVIO
HON. KARL CHRISTIAN F. VEGA
RUTH B. SOTTO

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1