## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2025
PROVINCE: PANGASINAN |  |  | QUARTER: | 2
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Econimic Development
LGU payment of Loan | Mapandan, Pangasinan | 25958787.24 | 2025-01-01 | 2025-12-01 | 43.92% | 11400898.1 |  | In process
LDF-Construction of One (1) Stop Shop Building Phase 4 | Brgy. Poblacion, Mapandan | 8500000 | 2025-01-01 | 2025-07-17 | 66.16% | 5623297.97 |  | In process
Environmental Management
TOTAL |  | 34458787.24 |  |  | 49.4% | 17024196.07
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
ANA MARICRIS B. NATAVIO | RUTH B. SOTTO , CPA |  |  | HON. KARL CHRISTIAN F. VEGA
Local Budget Officer | Municipal Accountant |  |  |  | Local Chief Executive

## Form 7 - DFU (2) (hidden)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2024
PROVINCE: PANGASINAN |  |  | QUARTER: | 4
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Econimic Development
Construction of Perimeter Fence, Backfilling and Concreting of Super Rural Health Unit's Ground | Brgy. Torres, Mapandan | 1500000 | 2024-09-01 | 2024-11-01 | 99.88% | 1498197.06 |  | COMPLETED
Construction of Cross/Drainage Canal along Gondol Street , Primicias | Brgy. Primicias, Mapandan | 500000 | 2024-05-13 | 2024-06-17 | 99.9% | 499480.61 |  | COMPLETED
Improvement/Extension of Office for MDRRM Command Center at Brgy. Poblacion | Brgy. Poblacion, Mapandan | 700000 | 2024-09-01 | 2024-12-01 | 0% | 0 |  | NOT YET PAID
Improvement/Re-painting of Roof of the Mapandan Municipal Hall | Brgy. Poblacion, Mapandan | 1700000 | 2024-03-28 | 2024-05-28 | 99.91% | 1698498.46 |  | COMPLETED
Re-conctruction of Drainage Canal along Pico Avenue at Brgy. Coral | Brgy. Coral, Mapandan | 500000 | 2024-05-13 | 2024-06-17 | 99.87% | 499354.81 |  | COMPLETED
Construction of Covered Drainage Canal along Lawin Avenue at Brgy. Poblacion | Brgy. Poblacion, Mapandan | 500000 | 2024-05-13 | 2024-06-17 | 99.86% | 499285.89 |  | COMPLETED
Procurement and Installation of Industrial Fan at Tulagan Multi-Purpose Gym | Brgy. Poblacion, Mapandan | 300000 | 2024-09-01 | 2024-10-01 | 99.86% | 298000 |  | COMPLETED
Construction of Airconditioned Waiting Sched at Poblacion Mapandan | Brgy. Poblacion, Mapandan | 500000 | 2024-09-01 | 2024-12-01 | 0% | 0 |  | NOT YET PAID
Impro. Brgy Road/Drianage-Orchid St. Nilombot Phase 3 | Brgy.Nilombot, Mapandan | 1000000 | 2024-05-13 | 2024-07-07 | 99.91% | 999113.99 |  | COMPLETED
LGU payment of Loan | Mapandan, Pangasinan | 21176026.09 | 2024-01-01 | 2024-12-01 | 100% | 20560750.94 |  | COMPLETED
Additional Illumination of Mapandan Town Plaza Phase 2 | Brgy. Poblacion, Mapandan | 571506.51 | 2024-05-13 | 2024-06-17 | 100% | 568293.91 |  | COMPLETED
Environmental Management
TOTAL |  | 28947532.6 |  |  | 93.69% | 27120975.67
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Local Budget Officer | Municipal Accountant |  |  |  | Local Chief Executive
ANA MARICRIS B. NATAVIO
HON. KARL CHRISTIAN F. VEGA
RUTH B. SOTTO

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1