## Form 7 - DFU (hidden)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2025
PROVINCE: PANGASINAN |  |  | QUARTER: | 2
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Econimic Development
LGU payment of Loan | Mapandan, Pangasinan | 25958787.24 | 2025-01-01 | 2025-12-01 | 43.92% | 11400898.1 |  | In process
LDF-Construction of One (1) Stop Shop Building Phase 4 | Brgy. Poblacion, Mapandan | 8500000 | 2025-01-01 | 2025-07-17 | 66.16% | 5623297.97 |  | In process
Environmental Management
TOTAL |  | 34458787.24 |  |  | 49.4% | 17024196.07
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
ANA MARICRIS B. NATAVIO | RUTH B. SOTTO , CPA |  |  | HON. KARL CHRISTIAN F. VEGA
Local Budget Officer | Municipal Accountant |  |  |  | Local Chief Executive

## Q3_2025 (hidden)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2025
PROVINCE: PANGASINAN |  |  | QUARTER: | 3
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Econimic Development
LGU payment of Loan | Mapandan, Pangasinan | 25958787.24 | 2025-01-01 | 2025-12-01 | 68.39% | 17754265.89 |  | In Process
LDF-Construction of One (1) Stop Shop Building Phase 4 | Brgy. Poblacion, Mapandan | 8500000 | 2025-01-01 | 2025-07-17 | 100% | 8497315.18 |  | Completed
Environmental Management
TOTAL |  | 34458787.24 |  |  | 76.18% | 26251581.07
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
ANA MARICRIS B. NATAVIO | RUTH B. SOTTO , CPA |  |  | HON. KARL CHRISTIAN F. VEGA
Local Budget Officer | Municipal Accountant |  |  |  | Local Chief Executive

## Q4_2025 (hidden)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2025
PROVINCE: PANGASINAN |  |  | QUARTER: | 4
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Econimic Development
LGU payment of Loan | Mapandan, Pangasinan | 25958787.24 | 2025-01-01 | 2025-12-01 | 100% | 24022083.98 |  | Completed
LDF-Construction of One (1) Stop Shop Building Phase 4 | Brgy. Poblacion, Mapandan | 8500000 | 2025-01-01 | 2025-07-17 | 100% | 8497315.18 |  | Completed
Environmental Management
TOTAL |  | 34458787.24 |  |  | 100% | 32519399.16
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
ANA MARICRIS B. NATAVIO | RUTH B. SOTTO , CPA |  |  | HON. KARL CHRISTIAN F. VEGA
Local Budget Officer | Municipal Accountant |  |  |  | Local Chief Executive

## Q1 2026
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2026
PROVINCE: PANGASINAN |  |  | QUARTER: | 1
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Econimic Development
Construction of One (1) Stop Shop Phase 5 | Brgy. Poblacion, Mapandan. | 6500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
LGU Payment of Loans | Mapandan, Pangasinan | 22695379.08 | 2026-01-01 | 2026-12-01 | 25.18% | 5714034.36 |  | In Process
Construction of Perimeter Fence, Backfilling and Concreting of Super Rural Health Unit's Ground Phase 2 | Brgy. Torres, Mapandan | 550000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Rehabilitation/Improvement of Mapandan Tennis Clubhouse inside Public Plaza and Comfort Room inside Public Auditorium | Brgy. Poblacion, Mapandan. | 950000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Stalls for Ambulant Vendors at Public Market | Brgy. Poblacion, Mapandan. | 625000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Sewerage Treatment Plant at Public Market | Brgy. Poblacion, Mapandan. | 1195000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Drainage Canal along Agila Street, Brgy. Amanoaoac | Brgy. Amanoaoac, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Drainage Canal along Apayas Street, Brgy. Apaya | Brgy. Apaya, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Drainage Canal along Caimito Street Ext. , Brgy. Aserda | Brgy. Aserda, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Improvement of Road Along Tibule St. Brgy. Baloling | Brgy. Baloling, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Drainage Canal along Pico Avenue, Brgy. Coral | Brgy. Coral, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Drainage Canal along Golden Shower Street, Brgy. Golden | Brgy. Golden., Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Drainage Canal along Wag-wag Street and Raminad Street, Brgy. Jimenez | Brgy.Jimenez, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Concrete Paving of Road along Chico Street Extension, Brgy. Luyan | Brgy. Luyan, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Concrete Paving of Road along Seniguelas Street, Brgy. Pias | Brgy. Pias, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Drainage Canal along Cadena de Amor Street, Brgy. Poblacion | Brgy. Poblacion, Mapandan. | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Drainage Canal along Gondol Street, Brgy. Primicias | Brgy. Primicias, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Drainage Canal along Sitio Sabangan, Brgy. Sta. Maria | Brgy. Sta. Maria, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Construction of Drainage Canal along Salumague Street Ext., Brgy. Torres | Brgy. Torres, Mapandan | 500000 |  | 2026-12-01 | 0% | 0 |  | Not yet started
Environmental Management
TOTAL |  | 39015379.08 |  |  | 14.65% | 5714034.36
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Sgd | Sgd |  |  |  | Sgd
ANA MARICRIS B. NATAVIO | RUTH B. SOTTO , CPA |  |  | HON. KARL CHRISTIAN F. VEGA
Local Budget Officer | Municipal Accountant |  |  |  | Local Chief Executive

## Form 7 - DFU (2) (hidden)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2024
PROVINCE: PANGASINAN |  |  | QUARTER: | 4
CITY/MUNICIPALITY: MUNICIPALITY OF MAPANDAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Econimic Development
Construction of Perimeter Fence, Backfilling and Concreting of Super Rural Health Unit's Ground | Brgy. Torres, Mapandan | 1500000 | 2024-09-01 | 2024-11-01 | 99.88% | 1498197.06 |  | COMPLETED
Construction of Cross/Drainage Canal along Gondol Street , Primicias | Brgy. Primicias, Mapandan | 500000 | 2024-05-13 | 2024-06-17 | 99.9% | 499480.61 |  | COMPLETED
Improvement/Extension of Office for MDRRM Command Center at Brgy. Poblacion | Brgy. Poblacion, Mapandan | 700000 | 2024-09-01 | 2024-12-01 | 0% | 0 |  | NOT YET PAID
Improvement/Re-painting of Roof of the Mapandan Municipal Hall | Brgy. Poblacion, Mapandan | 1700000 | 2024-03-28 | 2024-05-28 | 99.91% | 1698498.46 |  | COMPLETED
Re-conctruction of Drainage Canal along Pico Avenue at Brgy. Coral | Brgy. Coral, Mapandan | 500000 | 2024-05-13 | 2024-06-17 | 99.87% | 499354.81 |  | COMPLETED
Construction of Covered Drainage Canal along Lawin Avenue at Brgy. Poblacion | Brgy. Poblacion, Mapandan | 500000 | 2024-05-13 | 2024-06-17 | 99.86% | 499285.89 |  | COMPLETED
Procurement and Installation of Industrial Fan at Tulagan Multi-Purpose Gym | Brgy. Poblacion, Mapandan | 300000 | 2024-09-01 | 2024-10-01 | 99.86% | 298000 |  | COMPLETED
Construction of Airconditioned Waiting Sched at Poblacion Mapandan | Brgy. Poblacion, Mapandan | 500000 | 2024-09-01 | 2024-12-01 | 0% | 0 |  | NOT YET PAID
Impro. Brgy Road/Drianage-Orchid St. Nilombot Phase 3 | Brgy.Nilombot, Mapandan | 1000000 | 2024-05-13 | 2024-07-07 | 99.91% | 999113.99 |  | COMPLETED
LGU payment of Loan | Mapandan, Pangasinan | 21176026.09 | 2024-01-01 | 2024-12-01 | 100% | 20560750.94 |  | COMPLETED
Additional Illumination of Mapandan Town Plaza Phase 2 | Brgy. Poblacion, Mapandan | 571506.51 | 2024-05-13 | 2024-06-17 | 100% | 568293.91 |  | COMPLETED
Environmental Management
TOTAL |  | 28947532.6 |  |  | 93.69% | 27120975.67
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Local Budget Officer | Municipal Accountant |  |  |  | Local Chief Executive
ANA MARICRIS B. NATAVIO
HON. KARL CHRISTIAN F. VEGA
RUTH B. SOTTO

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1